## Sheet1
Task | Start Date | Days to complete
Data scraping | 2021-10-18 | 10
Data cleaning | 2021-10-22 | 12
Feature engineering | 2021-11-03 | 5
Algorithm research and study | 2021-11-08 | 4
Model development | 2021-11-12 | 10
Performance evaluation | 2021-11-22 | 7
Dimentionality reduction | 2021-11-22 | 7
Website development using flask | 2021-11-29 | 20
Deployment on heroku | 2021-12-19 | 5
Documentation | 2021-11-29 | 25
44487